## Registartion
Bug ID | Actor | Module Name | URL | Bug Description | Steps | Test Data | OS | Browser | Resolution Wise | Expected Result | Status | Assignee | Bug Priority | Remarks / Comments | Creation Date | Created By | Verified By | Verified Date
1 | Client | Registration | https://operator.knowork.xyz/register | Font of Login Link is Too Small | Step1: Go to register link |  | Windows 10 | In all Broswer | 1920*1080 | Font of login link should be proper | New | Developer | Low |  | 31/3/2022 | Jhanvi
2 | Client | Registration | https://operator.knowork.xyz/register | Validaion message for all field has different design | Step1: Go to register link |  | Windows 10 | Firefox: Version 98.0.2 (64-bit) | 1920*1080 |  | New | Developer | Low |  | 31/3/2022 | Jhanvi
3 | Client | Registration | https://operator.knowork.xyz/register | Eye Icon is missing for password and password confirmation field | Step1: Go to register link |  | Windows 10 | Firefox: Version 98.0.2 (64-bit) Chrome: Version 100.0.4896.60 (Official Build) (64-bit) | 1920*1080 | Eye icon should be available in password and password confirmation field | New | Developer | Low |  | 31/3/2022 | Jhanvi
4 | Client | Registration | https://operator.knowork.xyz/register | Font Color of Hyperlink of App Terms and Privacy Policy is not proper | Step1: Go to register link |  | Windows 10 | In all Broswer | 1920*1080 | Font color of hyperlink shpuld be proper | New | Developer | Low |  | 31/3/2022 | Jhanvi
5 | Client | Registration | https://operator.knowork.xyz/register | Login link is not visible | Step1: Go to register link |  | Windows 10 | In all Broswer | 1920*1080 | Color and size of login link should be proper | New | Developer | Low |  | 31/3/2022 | Jhanvi
6 | Client | Registration | https://operator.knowork.xyz/register | Page not fixed | Step1: Go to register link |  | Windows 10 | Edge: Version Version 99.0.1150.55(64-bit) | 1920*1080 | Page should be fitted in browser | New | Developer | Low |  | 31/3/2022 | Jhanvi
7 | Client | Registration | https://operator.knowork.xyz/register | System does not fire Validation message when email is blank | Step1: Go to register link Step2: Enter valid name Step3:Enter blank email Step4: Enter valid password Step5: Enter valid password confirmation Step6: Checkbox checked Step7: Click on Register Button | Name= "jhanvi" Email="" Password="123456" Password confirmation="123456" Checkbox="Checked" | Windows 10 | Firefox: Version 98.0.2 (64-bit) | 1920*1080 | System should fire validation message for Blank email "Please enter email." | New | Developer | Low |  | 31/3/2022 | Jhanvi
8 | Client | Registration | https://operator.knowork.xyz/register | System does not fire Validation message when password is blank | Step1: Go to register link Step2: Enter valid name Step3:Enter valid email Step4: Enter blank password Step5: Enter valid password confirmation Step6: Checkbox checked Step7: Click on Register Button | Name= "jhanvi" Email="jhanviasodiya+a12345@gmail.com" Password="" Password confirmation="123456" Checkbox="Checked" | Windows 10 | Firefox: Version 98.0.2 (64-bit) | 1920*1080 | System should fire validation message for Blank password "Please enter password." | New | Developer | Low |  | 31/3/2022 | Jhanvi
9 | Client | Registration | https://operator.knowork.xyz/register | System does not fire Validation message when name is blank | Step1: Go to register link Step2: Enter blank name Step3:Enter valid email Step4: Enter valid password Step5: Enter valid password confirmation Step6: Checkbox checked Step7: Click on Register Button | Name= "" Email="jhanviasodiya+a123456@gmail.com" Password="123456" Password confirmation="123456" Checkbox="Checked" | Windows 10 | Firefox: Version 98.0.2 (64-bit) | 1920*1080 | System should fire validation message for Blank name "Please enter name." | New | Developer | Low |  | 31/3/2022 | Jhanvi
10 | Client | Registration | https://operator.knowork.xyz/register | System does not fire Validation message when password confirmation is blank | Step1: Go to register link Step2: Enter valid name Step3:Enter valid email Step4: Enter valid password Step5: Enter blank password confirmation Step6: Checkbox checked Step7: Click on Register Button | Name= "jhanvi" Email="jhanviasodiya+a1234567@gmail.com" Password="123456" Password confirmation="" Checkbox="Checked" | Windows 10 | Firefox: Version 98.0.2 (64-bit) | 1920*1080 | System should fire validation message for Blank passsword confirmation "Please enter password confirmation." | New | Developer | Low |  | 31/3/2022 | Jhanvi
11 | Client | Registration | https://operator.knowork.xyz/register | Blank space accepted in password and password confirmation field | Step1: Go to register link Step2: Enter valid name Step3:Enter valid email Step4: Enter blank space in password Step5: Enter blank space in password confirmation Step6: Checkbox checked Step7: Click on Register Button | Name= "jhanvi" Email="jhanviasodiya+a12345678@gmail.com" Password=" " Password confirmation=" " Checkbox="Checked" | Windows 10 | In all browser | 1920*1080 | System should fire validation message "Please enter valid password and password confirmation." | New | Developer | Low |  | 31/3/2022 | Jhanvi
12 | Client | Registration | https://operator.knowork.xyz/register | Space b/w two words accepted in password and password confirmation field | Step1: Go to register link Step2: Enter valid name Step3:Enter valid email Step4: Enter space b/w two words in password Step5: Enter space b/w two words in password confirmation Step6: Checkbox checked Step7: Click on Register Button | Name= "jhanvi" Email="jhanviasodiya+a123456789@gmail.com" password="jhanvi asodiya" password confirmation="jhanvi asodiya" Checkbox="Checked" | Windows 10 | In all browser | 1920*1080 | System should fire validation message "Please enter valid password and password confirmation." | New | Developer | Low |  | 31/3/2022 | Jhanvi
13 | Client | Registration | https://operator.knowork.xyz/register | Special character accepted in name,password and password confirmation field | Step1: Go to register link Step2: Enter valid name Step3:Enter valid email Step4: Enter Speical character in password Step5: Enter Speical character in password confirmation Step6: Checkbox checked Step7: Click on Register Button | Name= "jhanvi" Email="jhanviasodiya+a12345000@gmail.com" password="@#$%" password confirmation="@#$%" Checkbox="Checked" | Windows 10 | In all browser | 1920*1080 | System should fire validation message "Please enter valid password and password confirmation." | New | Developer | Low |  | 31/3/2022 | Jhanvi
14 | Client | Registration | https://operator.knowork.xyz/register | Numeric value is accepted in password and password confirmation field | Step1: Go to register link Step2: Enter valid name Step3:Enter valid email Step4: Enter numeric in password Step5: Enter numeric in password confirmation Step6: Checkbox checked Step7: Click on Register Button | Name= "jhanvi" Email="jhanviasodiya+a12345111@gmail.com" password="123456" password confirmation="123456" Checkbox="Checked" | Windows 10 | In all browser | 1920*1080 | System should fire validation message "Please enter valid password and password confirmation." | New | Developer | Low |  | 31/3/2022 | Jhanvi
15 | Client | Registration | https://operator.knowork.xyz/register | Eye icon is dissappeared after enter password | Step1: Go to register link Step2: Enter valid name Step3:Enter valid email Step4: Enter password Step5: Enter password confirmation Step6: Click on Register Button | Name= "jhanvi" Email="jhanviasodiya+a1234511122@gmail.com" password="123456" password confirmation="123456" Checkbox="Checked" | Windows 10 | Edge: Version Version 99.0.1150.55(64-bit) | 1920*1080 | Eye icon should be available after enter the password | New | Developer | Low |  | 31/3/2022 | Jhanvi
16 | Client | Registration | https://operator.knowork.xyz/register | System does not fire validation message when email is invalid | Step1: Go to register link Step2: Enter invalid email Step4: Click on Register Button | Name= "1" Email="jhanviasodiya+a123451112@gmail.com" password="123456" password confirmation="123456" Checkbox="Checked" | Windows 10 | Firefox: Version 98.0.2 (64-bit) | 1920*1080 | System should fire validation message for invalid email "Please enter valid email." | New | Developer | Low |  | 31/3/2022 | Jhanvi
17 | Client | Registration | https://operator.knowork.xyz/register | Logo has diff color in mail box when system generated mail |  |  | Windows 10 | In all browser | 1920*1080 | Logo should be same | New | Developer | Low |  | 31/3/2022 | Jhanvi
18 | Client | Registration | https://operator.knowork.xyz/register | Validation message overlap in email field when user tap enter | Step1: Go to register link |  | Windows 10 | Chrome: Version 100.0.4896.60 (Official Build) (64-bit) Edge: Version 99.0.1150.55(64-bit) | 1920*1080 | Validation message should be in proper place | New | Developer | Low |  | 31/3/2022 | Jhanvi
Suggestions
1 | Client | Registration | https://operator.knowork.xyz/register | Validation message should be proper in every field

## Static Page
Bug ID | Actor | Module Name | URL | Bug Description | Steps | Test Data | OS | Browser | Resolution Wise | Expected Result | Status | Assignee | Bug Priority | Remarks / Comments | Creation Date | Created By | Verified By | Verified Date
1 | Client | Static Page |  | Select all events at a time |  |  | Windows 10 | In all browser | 1920*1080 |  | New | Developer | Low |  | 31/03/2022 | Jhanvi
2 | Client | Static Page |  | Redirect to Create space page Without select any event |  |  | Windows 10 | In all browser | 1920*1080 | System should fire validation message "Please select atleast one event" | New | Developer | Low |  | 31/03/2022 | Jhanvi
3 | Client | Static Page |  | Page not fitted when browser is minimize |  |  | Windows 10 | In all browser | 1920*1080 | Page should be fitted in browser | New | Developer | Low |  | 31/03/2022 | Jhanvi

## Create Space
Bug ID | Actor | Module Name | URL | Bug Description | Steps | Test Data | OS | Browser | Resolution Wise | Expected Result | Status | Assignee | Bug Priority | Remarks / Comments | Creation Date | Created By | Verified By | Verified Date
1 | Client | Create space | https://operator.knowork.xyz/register | Designing of browse button is diff | Step1: Go to Space form link |  | Windows 10 | Chrome: Version 100.0.4896.60 (Official Build) (64-bit) Edge: Version 99.0.1150.55(64-bit) | 1920*1080 | Designing of browse button should be proper | New | Developer | Low |  | 31/3/2022 | Jhanvi
2 | Client | Create space | https://operator.knowork.xyz/register | Font Color of Hyperlink of App Terms and Privacy Policy is not proper | Step1: Go to Space form link |  | Windows 10 | In all Broswer | 1920*1080 | Font color of hyperlink should be proper | New | Developer | Low |  | 31/3/2022 | Jhanvi
3 | Client | Create space | https://operator.knowork.xyz/register | Error occurred in re-send confirmation |  |  | Windows 10 | In all Broswer | 1920*1080 | Resend confirmation mail should be generated in mailbox | New | Developer | Medium |  | 31/3/2022 | Jhanvi
4 | Client | Create space | https://operator.knowork.xyz/register | Open create space page multiple times whenever click on activate knowork button in mail |  |  | Windows 10 | In all Broswer | 1920*1080 | Form should be open only once when click on activate knowork button | New | Developer | Low |  | 31/3/2022 | Jhanvi
5 | Client | Create space | https://operator.knowork.xyz/register | After registartion user can directly login without create this create space page |  |  | Windows 10 | In all Broswer | 1920*1080 | System should fire validation message"Please fill create first space form before login" | New | Developer | Low |  | 31/3/2022 | Jhanvi
6 | Client | Create space | https://operator.knowork.xyz/register | Successfully create space page and redirect to dashboard without check the checkbox | Step1: Go to Space form link Step2: Enter space name Step3: Enter subdomain Step4: Checkbox unchecked Step4:Click on send | Space name="a" Space domain="jhanvi" Checkbox="Unchecked" | Windows 10 | In all Broswer | 1920*1080 | System should fire validation message "Please check the checkbox" | New | Developer | Low |  | 31/3/2022 | Jhanvi
7 | Client | Create space | https://operator.knowork.xyz/register | Single alphabet accepted in space name and domain field | Step1: Go to Space form link Step2: Enter single alphabet in space name Step3: Enter single alphabet in subdomain Step4:Click on send | Space name="a" Space domain="" Checkbox="Unchecked" | Windows 10 | In all Broswer | 1920*1080 | System should fire validation message "Please enter valid space name and domain." | New | Developer | Low |  | 31/3/2022 | Jhanvi
8 | Client | Create space | https://operator.knowork.xyz/register | Page not fixed | Step1: Go to Space form link |  | Windows 10 | Edge: Version Version 99.0.1150.55(64-bit) | 1920*1080 | Page should be fixed in browser | New | Developer | Low |  | 31/3/2022 | Jhanvi
9 | Client | Create space | https://operator.knowork.xyz/register | Can't cancel image/pdf after uploaded logo | Step1: Go to Space form link |  | Windows 10 | In all Broswer | 1920*1080 |  | New | Developer | Low |  | 31/3/2022 | Jhanvi |  |  | 10240
10 | Client | Create space | https://operator.knowork.xyz/register | Does not preview when pdf file uploaded in logo | Step1: Go to Space form link |  | Windows 10 | In all Broswer | 1920*1080 | System should preview when pdf file uploaded | New | Developer | Low |  | 31/3/2022 | Jhanvi

## Login
Bug ID | Actor | Module Name | URL | Bug Description | Steps | Test Data | OS | Browser | Resolution Wise | Expected Result | Status | Assignee | Bug Priority | Remarks / Comments | Creation Date | Created By | Verified By | Verified Date
1 | Client | Login | https://operator.knowork.xyz/login | Validaion message for both field has different design | Step1:Go to Login Link |  | Windows 10 | Firefox: Version 98.0.2 (64-bit) | 1920*1080 | Design of validation message should be proper | New | Developer | Low |  | 31/3/2022 | Jhanvi
2 | Client | Login | https://operator.knowork.xyz/login | Eye Icon is missing for password field | Step1:Go to Login Link |  | Windows 10 | Firefox: Version 98.0.2 (64-bit) Chrome: Version 100.0.4896.60 (Official Build) (64-bit) | 1920*1080 | Eye icon should be there in password field | New | Developer | Low |  | 31/3/2022 | Jhanvi
3 | Client | Login | https://operator.knowork.xyz/login | Page not fixed | Step1:Go to Login Link |  | Windows 10 | Edge: Version Version 99.0.1150.55(64-bit) | 1920*1080 | Page should be fixed | New | Developer | Low |  | 31/3/2022 | Jhanvi
4 | Client | Login | https://operator.knowork.xyz/login | Font of Register Link is Too Small | Step1:Go to Login Link |  | Windows 10 | In all browser | 1920*1080 | Font of register link should be proper | New | Developer | Low |  | 31/3/2022 | Jhanvi
5 | Client | Login | https://operator.knowork.xyz/login | System does not fire Validation message when email and password is blank | Step1:Go to Login Link Step2:Enter blank email Step3:Enter blank password Step4:Click on Login | Email="" password="" | Windows 10 | Firefox: Version 98.0.2 (64-bit) | 1920*1080 | System should fire validation message "Please emter email and password" | New | Developer | Medium |  | 31/3/2022 | Jhanvi
6 | Client | Login | https://operator.knowork.xyz/login | Eye Icon is dissapeared for password field after enter the value | Step1:Go to Login Link Step2:Enter email Step3:Enter password Step4:Click on Login | Email="jhanviasodiya123@gmail.com" password="123456" | Windows 10 | Edge: Version Version 99.0.1150.55(64-bit) | 1920*1080 | Eye icon should b there after enter the password | New | Developer | Low |  | 31/3/2022 | Jhanvi
7 | Client | Login | https://operator.knowork.xyz/login | Validation message overlap in email field when user tap enter | Step1:Go to Login Link Step2:Enter email and tap enter | Email="jhanviasodiya123@gmail.com" password="123456" | Windows 10 | Chrome: Version 100.0.4896.60 (Official Build) (64-bit) Edge: Version 99.0.1150.55(64-bit) | 1920*1080 | Validation message should be in proper place | New | Developer | Low |  | 31/3/2022 | Jhanvi
8 | Client | Login | https://operator.knowork.xyz/login | Validation message overlap to login button when password is blank | Step1:Go to Login Link Step2:Enter email Step3:Enter blank password Step4:Click on Login | Email="jhanviasodiya123@gmail.com" password="" | Windows 10 | In all browser | 1920*1080 | Validation message should be in proper place | New | Developer | Low |  | 31/3/2022 | Jhanvi
Suggestions
1 | Client | Change Password | https://operator.knowork.xyz/login | Old passsword tab should be there

## Edit Profile
Bug ID | Actor | Module Name | URL | Bug Description | Steps | Test Data | OS | Browser | Resolution Wise | Expected Result | Status | Assignee | Bug Priority | Remarks / Comments | Creation Date | Created By | Verified By | Verified Date
1 | Client | Edit profile | https://operator.knowork.xyz/profile | Numeric,alpha numeric,single alphabet,Special character accepted in name, position and description | Step1:Go to My profile dropdown and click on edit profile link Step2:Enter numeric,alpha numeric,single alphabet and special character in name,position and description Step3:Click on save | Name="1" "_1" "a" "#" Position= "1" "_" "a" "#" Description="1" "_" "a" "#" | Windows 10 | In all browsers | 1920*1080 | System should fire validation message"Please enter valid name,position and description" | New | Developer | Medium |  | 2022-01-04 | Jhanvi
2 | Client | Edit profile | https://operator.knowork.xyz/profile | Validaion message for all field has different design | Step1:Go to My profile dropdown and click on edit profile link |  | Windows 10 | Firefox: Version 98.0.2 (64-bit) | 1920*1080 | Design of Validation message should be proper | New | Developer | Low |  | 2022-01-04 | Jhanvi
3 | Client | Edit profile | https://operator.knowork.xyz/profile | Multiple times popup generated when click on save | Step1:Go to My profile dropdown and click on edit profile link Step2:Enter Name Step3:Enter Position Step4:Enter Description Step5:Click on save | Name="jhanvi" Position= "QA" Description="jhanvi asodiya" | Windows 10 | In all browsers | 1920*1080 | System should be generated only one popup when click on save | New | Developer | Low |  | 2022-01-04 | Jhanvi
4 | Client | Edit profile | https://operator.knowork.xyz/profile | popup generated "error"in right top side when in name field user enter blank space | Step1:Go to My profile dropdown and click on edit profile link Step2:Enter Blank Space in Name Step3:Enter Position Step4:Enter Description Step5:Click on save | Name=" " Position= "QA" Description="jhanvi asodiya" | Windows 10 | In all browsers | 1920*1080 |  | New | Developer | Low |  | 2022-01-04 | Jhanvi
5 | Client | Edit profile | https://operator.knowork.xyz/profile | Blank space accepted in position and description | Step1:Go to My profile dropdown and click on edit profile link Step2:Enter Name Step2:Enter Blank Space in Position Step3:Enter Blank Space in Description Step4:Click on save | Name="Jhanvi" Postion=" " Description=" " | Windows 10 | In all browsers | 1920*1080 | System should fire validation message"Please enter valid position and description" | New | Developer | Medium |  | 2022-01-04 | Jhanvi
6 | Client | Edit profile | https://operator.knowork.xyz/profile | Designing of browse button is diff | Step1:Go to My profile dropdown and click on edit profile link |  | Windows 10 | Chrome: Version 100.0.4896.60 (Official Build) (64-bit) Edge: Version 99.0.1150.55(64-bit) | 1920*1080 | Designing of browse button should be proper | New | Developer | Low |  | 2022-01-04 | Jhanvi
7 | Client | Edit profile | https://operator.knowork.xyz/profile | Can't cancel image/pdf after uploaded in avatar | Step1:Go to My profile dropdown and click on edit profile link |  | Windows 10 | In all browsers | 1920*1080 |  | New | Developer | Medium |  | 2022-01-04 | Jhanvi
8 | Client | Edit profile | https://operator.knowork.xyz/profile | After refresh the page data saved in browser(not gone) | Step1:Go to My profile dropdown and click on edit profile link |  | Windows 10 | In all browsers | 1920*1080 | Data should be gone after refresh the page | New | Developer | Medium |  | 2022-01-04 | Jhanvi
9 | Client | Edit profile | https://operator.knowork.xyz/profile | PDF file not preview in avtar field | Step1:Go to My profile dropdown and click on edit profile link Step2:Upload image/pdf in Avatar field Step3: Click on Save |  | Windows 10 | In all browsers | 1920*1080 | Pdf file should be preview in avtar field | New | Developer | Low |  | 2022-01-04 | Jhanvi
10 | Client | Edit profile | https://operator.knowork.xyz/profile | Can't drag and drop pdf file in avtar field | Step1:Go to My profile dropdown and click on edit profile link Step2:Drag pdf in Avatar field Step3: Click on Save |  | Windows 10 | In all browsers | 1920*1080 | Pdf file should be drag and dropped in avtar field | New | Developer | Low |  | 2022-01-04 | Jhanvi
11 | Client | Edit profile | https://operator.knowork.xyz/profile | Text dissapered when hover on edit profile from menu | Step1:Go to My profile dropdown and click on edit profile link |  | Windows 10 | In all browsers | 1920*1080 | Text should be proper when hover on change password | New | Developer | Low |  | 2022-01-04 | Jhanvi
12 | Client | Edit profile | https://operator.knowork.xyz/profile | Font Color of Hyperlink in footer is not proper | Step1:Go to My profile dropdown and click on edit profile link |  | Windows 10 | In all browsers | 1920*1080 | Font color of hyperlink should be proper | New | Developer | Low |  | 2022-01-04 | Jhanvi
13 | Client | Edit profile | https://operator.knowork.xyz/profile | Validation message is not in proper place | Step1:Go to My profile dropdown and click on edit profile link Step2: Enter blank name Step3:Click on save |  | Windows 10 | Firefox: Version 98.0.2 (64-bit) Edge: | 1920*1080 | In browser valiadtion message should be in proper place | New | Developer | Low |  | 2022-01-04 | Jhanvi
Suggestions
1 | Client | Edit Profile | https://operator.knowork.xyz/profile | Email and company name should be non editable
2 | Client | Edit Profile | https://operator.knowork.xyz/profile | after uploading image/pdf/video and click on save it will take too time and load
3 | Client | Edit Profile | https://operator.knowork.xyz/profile | Validation message should be proper in name field

## Change Password
Bug ID | Actor | Module Name | URL | Bug Description | Steps | Test Data | OS | Browser | Resolution Wise | Expected Result | Status | Assignee | Bug Priority | Remarks / Comments | Creation Date | Created By | Verified By | Verified Date
1 | Client | Change Password | https://operator.knowork.xyz/password | Validaion message for all field has different design | Step1: Click on Change password link |  | Windows 10 | Firefox: Version 98.0.2 (64-bit) | 1920*1080 | Design of validation message should be proper | New | Developer | Low |  | 2022-01-04 | Jhanvi
2 | Client | Change Password | https://operator.knowork.xyz/password | Eye icon is dissappeared after enter password | Step1: Click on Change password link Step2: Enter Password Step3:Save | Password="123456" | Windows 10 | Edge: Version 99.0.1150.55(64-bit) | 1920*1080 | Eye icon should b there after enter the password | New | Developer | Medium |  | 2022-01-04 | Jhanvi
3 | Client | Change Password | https://operator.knowork.xyz/password | numeric value,special character and alphanumeric value accepted in password and confirm password field | Step1: Click on Change password link Step2: Enter numeric,special character and alpha numeric value in Password and confirm password field Step3:Save | Password="123456" "$$$" "_12" Confirm password="123456" "$$$$$$" "__@3" | Windows 10 | In all browser | 1920*1080 | System should fire validation message "Please enter valid password and confirm password" | New | Developer | Medium |  | 2022-01-04 | Jhanvi
4 | Client | Change Password | https://operator.knowork.xyz/password | Page is not fitted | Step1: Click on Change password link |  | Windows 10 | Edge: Version 99.0.1150.55(64-bit) | 1920*1080 | Page should be fitted in browser | New | Developer | Medium |  | 2022-01-04 | Jhanvi
5 | Client | Change Password | https://operator.knowork.xyz/password | Blank Space accepted in both field | Step1: Click on Change password link Step2: Enter blank space in Password and confirm password field Step3:Save | Password=" " Confirm Password=" " | Windows 10 | In all browser | 1920*1080 | System should fire validation message "Please enter valid password and confirm password" | New | Developer | Medium |  | 2022-01-04 | Jhanvi
6 | Client | Change Password | https://operator.knowork.xyz/password | Validation message is not at proper place | Step1: Click on Change password link Step2: Enter blank Password and confirm password field Step3:Save | Password=" " Confirm Password=" " | Windows 10 | In all browser | 1920*1080 | Validation message should be in proper place | New | Developer | Low |  | 2022-01-04 | Jhanvi
7 | Client | Change Password | https://operator.knowork.xyz/password | Font Color of Hyperlink in footer is not proper | Step1: Click on Change password link |  | Windows 10 | In all browser | 1920*1080 | Font color of hyperlink should be proper | New | Developer | Low |  | 2022-01-04 | Jhanvi
8 | Client | Change Password | https://operator.knowork.xyz/password | Accepted new password same as a old password | Step1: Click on Change password link Step2: Enter old in Password and confirm password field Step3:Save | Old pw="123456 New pw="123456" | Windows 10 | In all browser | 1920*1080 | New password should be diff | New | Developer | Low |  | 2022-01-04 | Jhanvi
9 | Client | Change Password | https://operator.knowork.xyz/password | 2 validation message generated when password field blank and press enter | Step1: Click on Change password link Step2: Enter blank Password and confirm password field Step3:Press enter | Password="" Confirm Password="" | Windows 10 | Edge: Version 99.0.1150.55(64-bit) | 1920*1080 |  | New | Developer | Low |  | 2022-01-04 | Jhanvi
10 | Client | Change Password | https://operator.knowork.xyz/password | Text dissapered when hover on change password from menu | Step1: Click on Change password link |  | Windows 10 | In all browser | 1920*1080 | Text should be proper when hover on change password | New | Developer | Low |  | 2022-01-04 | Jhanvi
11 | Client | Change Password | https://operator.knowork.xyz/password | Multiple times popup generated when click on save | Step1: Click on Change password link Step2: Enter Password and confirm password field Step3:Click on save |  | Windows 10 | In all browser | 1920*1080 | Popup should be generated once | New | Developer | Low |  | 2022-01-04 | Jhanvi
12 | Client | Change Password | https://operator.knowork.xyz/password | popup generated "error"in right top side when user enter invalid data in both field | Step1: Click on Change password link Step2: Enter invalid Password and confirm password field Step3:Click on save | Password="@@" Confirm Password="@@" | Windows 10 | In all browser | 1920*1080 |  | New | Developer | Low |  | 2022-01-04 | Jhanvi
13 | Client | Change Password | https://operator.knowork.xyz/password | Eye Icon is missing for all field | Step1: Click on Change password link |  | Windows 10 | Firefox: Version 98.0.2 (64-bit) Chrome: Version 100.0.4896.60 (Official Build) (64-bit) | 1920*1080 | Eye icon should be there in both field | New | Developer | Medium |  | 2022-01-04 | Jhanvi
14 | Client | Change Password | https://operator.knowork.xyz/password | Footer content is not in a proper place | Step1: Click on Change password link |  | Windows 10 | In all browser | 1920*1080 | Footer content should be in proper place | New | Developer | Low |  | 2022-01-04 | Jhanvi
Suggestions
1 | Client | Change Password |  | Old passsword tab should be there